## Tool Kit Overview
COVID-19 Strategic Planning Tool Kit for Education and Nonprofit Leaders
2020-04-01
Context
We recognize that strategic planning is both difficult and essential during this time of crisis. Bellwether recommends a simple, four phase planning approach (outlined below) to cut through the noise and focus limited time, energy, and resources.
The purpose of this Excel file is to provide "ready to use" planning templates (one per tab) aligned to this approach.
How to Use This Toolkit
Review the four phases outlined in the table below. Then move to the next tab to access the planning template for Phase 1: Reground. Follow the directions written in red, and fill in the light grey cells with your team's responses. Examples are provided in blue to support your thinking. Repeat this process for each tabs in this toolkit. You may want to upload this file to Google Sheets to allow collaboration on the templates across your team.
Phase | Essential Question | Why It Matters | Tool | Description
1. REGROUND. | What is our purpose and what does this mean for how we respond in this moment? | Your mission, vision, and core values can serve as your “North Star” and a lens through which you make tough decisions. | North Star Protocol | This “ready to use” meeting protocol will reground your team in your organizational “why” and then lead you through a structured brainstorming process to establish guiding principles for this time.
2. PRIORITIZE. | If we only get a few things right over the next few days, weeks, and months, what should they be? | Certain things matter more than others, particularly during a crisis. Decide what is absolutely essential to get right and focus there. | Prioritization Protocol | This protocol will push your team to sort through both the short and long term, and then relentlessly prioritize, ensuring focus on the most urgent and high-leverage work. You will leave aligned on a handful of short-term priorities that will drive your focus in the weeks ahead.
3. PLAN. | How will we organize ourselves to ensure we deliver on our priorities? | Moving to action during such uncertainty is a challenge. Develop simple and actionable plans, but remain flexible. | Work Plan Tool | Work plans break down projects into manageable steps with clear owners and outlined goals. This project planning template will help your team get specific about the tasks, timelines, and owners necessary to drive the work forward.
4. CONNECT. | How will we connect with others to communicate our plan efficiently, effectively, and with empathy? | Connection is key during moments of challenge. Provide clear, frequent, and empathetic communication and opportunities for community-building. | Stakeholder Engagement Map | Use this tool to identify all essential stakeholder groups, consider their needs, and plan to successfully connect with them throughout this crisis. You’ll plan for the format, frequency, and type of communication each group needs.
Acknowledgements
Bellwether Education Partners would like to thank all of the education and nonprofit leaders, teachers, and school staff who are working hard on behalf of students during this extremely trying time. We hope this toolkit is a helpful resource as you make decisions and plan in the midst of uncertainty. Thank you to the Bellwether teammates who contributed to the development of this resource, including but not limited to Lina Bankert, Andrew Rotherham, Alyssa Schwenk, Tanya Paperny, and Jeff Schulz. Any errors are the responsibility of the authors alone. For more information, email contactus@bellwethereducation.org.
Authors
Tresha Ward, Partner
Stephanie Spangler, Consultant
Katie Rouse, Senior Associate Partner
Eleisha Nelson-Reed, Associate Partner

## 1. Reground
COVID-19 Strategic Planning Tool Kit for Education and Nonprofit Leaders
Phase 1: Reground in Your "Why"
Tool: North Star Meeting Protocol
Step 1: Pull up your organization's mission, vision, and/or core values. Copy and paste below for reference.
Mission:
Vision:
Core Values:
Step 2: Using the above as a guide, reflect on the following questions as a leadership team.
- Why do we exist?
- What mission are we trying to fulfill?
- What is the thing we do best? How can we leverage that in this moment?
- What are our stated values and how will we, as a community, embody them at this moment?
- What does all of this mean for how we will respond to this crisis?
Step 3: Based on your conversation, list a handful of your core organizational values and then use those to identify guiding principles for how you will respond in the next several months.
Core Value |  | Guiding Principles
Example: "We meet the needs of all learners." |  | Our plan will keep English Language Learner and Special Education students front and center.
Example: "We develop the whole child." |  | Our plan will maintain access to social workers and counselors, and extend and give grace to our community.

## 2. Prioritize
COVID-19 Strategic Planning Tool Kit for Education and Nonprofit Leaders
Phase 2: Prioritize
Tool: Prioritization Protocol
Step 1: With your guiding principles in mind, describe what success looks like for your organization over various time horizons (next week, next month, next school year).
Step 2: With this definition of success in mind, identify NO MORE than four key priorities that your team MUST get right to achieve this success. This is intended to focus your resources. You can't do it all, so think about what the handful of most important priorities are. Record those in Column D.
Note: The longer-term portions of this table will serve as a "parking lot" for capturing work that will inform detailed work planning in later weeks. For example, for next school year to be successful, your school might need to consider hiring in a virtual climate. While important to capture/consider, this longer-term priority may not be necessary to move forward at this moment.
Time Horizon | Definition of Success | Key Priorities
Next Week | We need to make sure all our students are safe and healthy, and have access to basic necessities. We also need to set up the infrastructure to launch e-learning, which includes all our students having the devices and internet to log on. We also want to make sure we are clearly communicating expectations to staff for this time to ensure they are bought in and clear on the direction we are going. | 1. Launch Food Distribution Program | The next tab will focus on detailed work planning for these priorities.
2. Ensure All Students Have Devices/Internet
3. Provide Planning Supports/Clear Expectations for E-Teaching
4
Next Month |  | 1
2
3
4
Next School Year |  | 1
2
3
4

## 3. Plan
COVID-19 Strategic Planning Tool Kit for Education and Nonprofit Leaders
Phase 3: Plan
Tool: Work Plan
Step 1: Now we will create a detailed work plan around your short-term priorities your team defined on Tab 2 (automatically pulled below). Begin by assigning a clear owner who is responsible for ensuring each happens successfully.
Short Term Priorities |  | Owner
1. Launch Food Distribution Program
2. Ensure All Students Have Devices/Internet
3. Provide Planning Supports/Clear Expectations for E-Teaching
4
Step 2: Each priority owner should think about the work that needs to happen to achieve their priority. For each priority, list the concrete action steps (3-5), resources, owners, and deadlines needed. Review and refine as a group.
Short-Term Priority | Task | Resources Needed | Owner | Deadline | Status
1. Launch Food Distribution Program | Staff Schedule for Food Distribution Center | Avaliable Staff | Steph | 2020-04-01 | To Do
1. Launch Food Distribution Program | Create Family Contact List for Robo Calls | Contact Bank | Eleisha | 2020-04-01 | To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do

## 4. Connect
COVID-19 Strategic Planning Tool Kit for Education and Nonprofit Leaders
Phase 4: Connect
Tool: Stakeholder Engagement Plan
Step 1: Revise the list of stakeholders provided in Column B to reflect the most important stakeholders for your community.
Step 2: Consider your short-term priorities from the previous tabs. What does each stakeholder group need to know related to these key priorities? (Column C). Then, with your guiding principles from Tab 1 in mind, reflect on how you want each stakeholder group to feel at the end of their communication. Record in Column D.
Step 3: Combine the information in Column C with the intended impact in Column D to draft key messages for each stakeholder group.
Step 4: Determine the frequency, format, and owner for each of these key messages.
Stakeholders | What Do They Need to Know? | How Do We Want Them To Feel? | Key Messages | Frequency | Format | Owner
Teachers | The plan for e-teaching, their role, and expectations | Cared for personally, clear on details, rallied behind our mission, empowered to develop, innovate and execute plans | (Note: Write out your specific language.) — Acknowledge moment. — Connect one to two values/mission and what they mean to the organization in this moment. — Share supports for team during this time. — Share logistics for e-learning with clear expectations for what success looks like in the first week. | Two times during the planning week | Virtual team meetings | School leader
Staff
Families
Students
Community Partners
Government (e.g., mayor's office, state board of education, governor)