## Overview
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
August 2020
Context
In May, we released a popular tool to help school leaders reorient their focus from initial COVID-19 triage response to planning for reopening. Now with school starting in most places in the next few weeks, leaders need support at an even more detailed level. This complementary new resource is intended as a one-stop shop to help leaders complete their reopening plans, regardless of where they are in the planning process. This workbook includes all the components of a reopening plan, offers questions school leaders should address, and provides links to concrete resources and examples of completed plans as guides.
How to Use This Tool Kit
This Excel file provides ready-to-use planning templates to guide your team through each phase of our planning framework. You may want to upload this file to a shared drive to facilitate collaboration with your full planning team. Feel free to revise or modify this tool kit as you see fit.
Begin by reviewing the four-step planning framework outlined below to understand the overall approach and rationale, and then move on to the first tab. Follow the directions written in red, and fill in the light-yellow cells with your team's responses. Examples are provided in blue to support your thinking, but you can erase them as you fill in your own information. Repeat this process for each of the tabs in this tool kit.
A Note:
If you are seeking more foundational tools (including frameworks to help your team step back, reground, and prepare to move forward), please download Bellwether's Essential Planning workbook, |  | linked here.
Step | Description | Tool | Description
1. PRIORITIZE. | During the course of the year, schools must be prepared to shift between in-person, distance, and hybrid scenarios. Right now, leaders should be focused on planning for two scenarios: the one selected to start the year, plus the most likely contingency scenario. This worksheet will help ensure you're focused on the right primary/most likely scenario and contingency scenario. To help you do that, you will be first guided through a set of essential questions to help you lay out the key design constraints that will inform and guide your choice of scenario to prioritize your planning. | Prioritize
2. ORGANIZE. | This worksheet lists the components that any reopening plan should include. It should be used as a comprehensive checklist to make sure all components have been developed or are in development. For any components not yet complete, it can be used to assign owners, timelines, and ways of working across and within teams for completing the development of the plan. | Work Plan
3. PLAN. | This series of worksheets provides more detail on what each section of the plan should include. It lists the essential questions to answer and includes links to helpful resources. These worksheets should help the owners of the planning work ensure they have a complete understanding of what a comprehensive plan should include and what "good" looks like. | Operations
Culture
Academics
Talent
4. COMMUNICATE. | This worksheet can be used to ensure there is a simple communication plan to ensure all essential stakeholder groups are receiving the communication they need to support a successful start of the school year. | Communication Plan
Acknowledgements
Bellwether Education Partners would like to thank NewSchools Venture Fund for their funding and support of this resource. All errors are the responsibility of the authors alone.
We would also like to thank all the education and nonprofit leaders, teachers, and school staff who are working hard on behalf of students during this extremely trying time. We hope this complementary tool kit is a helpful resource as you make decisions and plan in the midst of uncertainty.
For more information, email contactus@bellwethereducation.org.

## 1. Prioritize
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 1: Prioritize
Tool: Prioritize Your Scenarios
Purpose of this tab: This page is intended to help you narrow in on the key scenario(s) you should prioritize planning for in reopening.
Step 1: For each constraint, write down what you know in Column D.
Step 2: Consider what else you might do to validate or refine each constraint, and capture those ideas in Column E.
Step 3: As a team, discuss what potential solutions for easing each constraint may be, and capture those emerging ideas in Column F.
Essential Constraint | Why It Matters | What do you already know? | How might you find out this information? What else might inform this constraint? | Are there creative or immediate solutions to explore for easing this constraint?
When will your students and staff return to school (start date)? | Informs timeline of planning | e.g., August 3, along with district guidelines | e.g., District or state guidelines | e.g., Request a different start date from the district and add extra days onto end of year
How many of your staff and students have articulated an intention to return in person? | Informs which scenario to prioritize upon return (e.g., in person, virtual, hybrid), and scheduling and staffing across scenarios | e.g., X out of Y staff will return in person; e.g., X out of Y students will return in person | e.g., Survey of staff and students, contracts with unions | e.g., Volunteers, partnering with community orgs or nonprofits to increase capacity
Of your staff, how many certified, uncertified, or subject matter experts have articulated an intention to return in person? | Informs which scenario to prioritize upon return (e.g., in person, virtual, hybrid), and scheduling and staffing across scenarios | e.g., All teachers with 10+ years of teaching experience will not return in person | e.g., Survey of staff and students, contracts with unions | e.g., Volunteers, partnering with community orgs or nonprofits to increase capacity
What is your building's capacity, under your local social distancing guidelines? | Drives how many students can attend in person, and therefore scheduling/staffing for in-person planning | e.g., 50% capacity (or X students) | e.g., Building floor plans, class rosters (given in-person registration), local distancing guidelines | e.g., Exploring outdoor space (weather permitting)
What is your capacity to transport students to & from school, under local social distancing guidelines? | Drives how many students can attend in person, and therefore scheduling and staffing for in-person planning | e.g., 25% capacity (or X students) | e.g., Busing contracts, local distancing guidelines | e.g., Double running routes, staggered arrivals/departures, bus "pools" with neighboring schools, hiring private vans
What is your budget? | Dictates how to prioritize spending on investments for new health & safety protocols, virtual curriculum & training, etc. | e.g., Forecasting ~5% cut in budget | e.g., District guidance | e.g., Raise additional philanthropy, tap into cash reserves
(IF APPLICABLE) What other requirements have your local authorities set with regards to reopening? | Informs the structure of your plan | e.g., All reopening plans must have all students in school at least 50% of the time | e.g., State governor's mandates
Step 4: Next, consider the following distinct scenarios:
Scenario | Description | Implications | What This Could Look Like
100% In Person | The majority of staff and students return to school in person, with new norms and policies around health and safety. | Operations must be significantly adjusted to maximize health and safety. A small but significant number of students and faculty are unable to return to campus.
100% Distance | Due to the high infection rate and increasing uncertainty, we decide to transition our entire learning service online. | While limited in-person interactions may persist on campus, primarily for teaching and leadership staff, the campus remains closed to students and the broader community.
Hybrid | While facilities reopen to some staff and students, the population remains divided between those who work from home and those who come to school. | A sizable number of families might opt out of returning to campus, or school leadership/government policy may require splitting the population as a safety imperative. | Examples of split schedules: AM/PM schedule, Days of the week, Weekly rotations Examples of student groupings: Grade-level (e.g., K-2 in person, 3-5 remote); High-need/most vulnerable (e.g., IEP/504s in person)
Step 5: Based on the constraints above, determine which scenario is MOST LIKELY for your school to start with in the fall. Then, determine which is your most likely "fall-back"/alternate scenario. Document both below, along with your thinking/rationale.
Priority | Scenario | Why This Scenario
Top | 100% In Person | Bulk of students and staff would like to return in person; building has 2x capacity to house all students safely even with social distancing
Alternate | 100% Distance | For rolling closures, we will need to define a 100% virtual plan

## 2. Organize
[6 empty] | Complete | In Progress | Not Yet Started
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 2: Organize
Tool: Work Plan to Guide Plan Development
Purpose of this tab: This page is intended to serve as a workplan and dashboard — for you to take stock of where you are, to orient you and your team to what work lies ahead, and to ensure that work will get done by the planned date.
Step 1: Consider the following workplan components. Determine when the ideal completion date will be, working backward from your target start date.
- Based on current guidance, when is the scheduled first day of school for students? - What date are teachers expected to return for professional development? - Is a reopening plan due to a board and/or public agency by a specific date? Based on the above, by when must the essential components of the reopening plan be developed?
Step 2: For each plan component, assign a clear owner who is responsible for ensuring this component happens successfully. The owner should then work within the detailed plan checklists that follow this tab (Operations, Culture, Academics, Talent) to flesh out these plan components. This owner should update the "Status" (in Column G on this tab) for each of these plan components based on the progress of the work on the detail tabs.
Step 3: You may refer to this tab as often as needed to see the "snapshot" or dashboard of progress you and your team are making toward completion of the plan.
Plan | Plan Component | Description | Target Completion Date | Owner | Status
General Planning | Prioritize | Which back-to-school scenario will be most critical for you and your team to plan for in the fall? What are the design constraints that will inform and guide this decision? |  |  | In Progress
| Organize | This document — what is the full scope of work that must be complete before reopening? How will I organize my team to get this work done in an efficient and timely manner? |  |  | In Progress
| Connect | When they are completed, how will I communicate these reopening plans to our most critical stakeholders (e.g., families, staff)? |  |  | In Progress
Operations | New health & safety protocols | What new health and safety protocols (e.g., masks, social distancing, ventilation, hygiene) must be in place for a safe reopening? |  |  | In Progress
| Incident response and contingency plans | What factors would trigger a switch across scenarios? What rapid response protocols and contingency plans need to be in place (e.g., if a child gets sick)? |  |  | In Progress
| Safeguarding the student journey from home to school | How will student travel and transition into the building need to look different to ensure safety and health for our staff and students? |  |  | In Progress
| Building operations | What changes to my building operations (e.g., common spaces, restrooms, hallways) need to be in place for a safe reopening? |  |  | In Progress
| Reimagining & redesigning the in-school experience | How will the school day need to change (e.g., meals, recess, gym) to ensure safety and health of our staff and students? |  |  | In Progress
| Fiscal | What is the expected impact on our budget? |  |  | In Progress
Culture | School culture | What does an essential student culture experience look like this fall? What changes and additions to the school culture model (e.g., mindsets & beliefs, methods and systems for building staff and student culture) will need to be considered to bring this student experience to life? |  |  | In Progress
| Staff and student supports | What wellness supports are needed for students and staff at this time? |  |  | In Progress
| Student, family, and community engagement | What changes and additions to student, family, and community supports (e.g., SEL, wraparound services, remote learning services) will need to be in place to support all students? |  |  | In Progress
Academics | Instructional model | What does an essential student academic experience look like this fall? What changes and additions to the instructional model (e.g., content/curriculum, delivery format, assessment, grading and accountability) will need to be considered to bring this student experience to life? |  |  | In Progress
| Schedule and staffing | Given constraints, what will the new academic schedule look like? What will staffing and coverage look like? |  |  | In Progress
| Student instructional supports | What changes and additions to student supports (e.g., academic interventions, ELL supports, special education supports) will need to be considered for flexibility and adaptability across scenarios? |  |  | In Progress
Talent | Staff policies & procedures | What staffing policies and procedures must be added or updated for COVID-19? |  |  | In Progress
| Professional development and support | What changes and additions to PD, ongoing teacher supports are critical during this time? |  |  | In Progress
Step 4: For each plan, align on: who will be on the planning team (and if dividing the work into teams, who will serve/lead which sub-team), how often to meet, and for how long.
Plan | Team Lead | Who Should Be On This Team? | How Often Should We Meet and When? | For How Long Should We Meet?
General Planning | e.g., Executive Director | e.g., Executive Director, Principal, APs, Teacher, Parent; leads of sub-teams | e.g., 2x weekly: - On Mondays to align on weekly priorities and sub-teams' work plans - On Fridays to hear updates/problem-solve on progress | e.g., 90 minutes
Operations | e.g., Director of Operations | e.g., Executive Director, Director of Operations, AP
Talent | e.g., Director of Talent | e.g., Executive Director, Director of Talent, Director of Curriculum, Teacher
Academic | e.g., Director of Curriculum | e.g., Executive Director, Director of Curriculum, Department Leads
Culture | e.g., Director of Culture | e.g., Executive Director, Director of Culture, Department Leads, Teacher
BW Note: | A general planning team usually consists of the school/network leadership team, and, if possible, a parent and teacher. If a teacher or parent is not on the team, there should be specific touchpoints to regularly solicit insight from these stakeholders. Some schools find an advisory group structure helpful for this purpose.

## 3. Plan Operations
[7 empty] | Complete | In Progress | Not Yet Started
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 3: Plan
Tool: Operations Checklist
Step 1: Default to your top priority scenario, and map out plans that address the components, essential topics, and essential questions in columns C-E below. You may find it helpful to reference the resources listed in Column H. As you plan each component/topic, remember to consider:
- Where can we build for adaptability (flexibility) so that the plans we develop allow us to move between scenarios without significant rework? (i.e., flex weeks) - Where do we need to reserve the right to play (build out several contingencies) by considering what distinct planning might be necessary across the multiple scenarios? (budget scenario planning in response to 1%, 3%, or 5% cuts)
Step 2: Determine where you will document and store your plans. Many teams we work with like to create a single folder on a shared drive. If that makes sense for your team, link the folder or section of the master deliverable in Column G.
Step 3: Once you have addressed all components within this plan for your top priority scenario, now consider your secondary/alternate scenario:
- identify which components of this plan are most critical to build additional contingency plans in, vs. which will be flexible enough to hold across scenarios; build out those contingency plans where necessary.
Note: If you would like additional details to support answering the Essential Questions listed in Column E, please refer to this Google Sheet.
Plan | Component | Essential Topics | Essential Questions to Address | Status | Link to Deliverable or Section of Master Plan | Key Resources
Operations | New health & safety protocols | New health and safety protocols | 1. What is your plan for social distancing? 2. What is your plan for sanitation, ventilation, and hygiene? 3. What is your protocol for screening and illness before students and staff are allowed to return in person? | Not Yet Started |  | Resource: CDC Interim Guidance for Child Care Programs and K-12 Schools
Resource: Risk Reduction Strategies for Reopening Schools
Resource: Reopening Schools in the Context of COVID-19: Health and Safety Guidelines from Other Countries
Example: Comp Sci HS COVID-19 Operations Plan, Part II. Methods of Risk Reduction
Example: Coney Island Prep Back to School Blueprint, "Health & Safety Protocols"
Example: KY DOE Phase II Reopening Considerations for Facilities
Example: TFS Social Distancing Guidelines and YouTube video
| Incident response and contingency plans | Alternative scenario & contingency plan | 1. What factors would trigger a switch across scenarios? Factors might include state or region moving into Phase 3, positivity rates increasing by a certain %, a threshold of staff or students reporting sick. 2. What is the contingency staffing plan for if there is a suspected or confirmed case of COVID-19 in the building? | In Progress |  | Example: Vermont DOE Technical Guidance for Local School Officials
Example: Comp Sci HS COVID-19 Operations Plan, Part IV. Incident Response
|  | Incident response plan | 1. Who on the team will coordinate the response in the event of a suspected or confirmed infection? 2. In the event of a suspected or confirmed infection, how will communications be coordinated with families, students, and the public health office and other public agencies? | Complete |  | Example: COVID Response Process Flow Template
Example: Comp Sci HS COVID-19 Operations Plan, Part IV. Incident Response
| Safeguarding the student journey from home to school | Transportation plan | 1. How will you coordinate with the district, other schools in the network, etc., to provide transportation for students? 2. What health & safety guidelines (e.g., socially distanced seating) will apply? |  |  | Resource: Getting Kids to School: Tackling the COVID-19 Transportation Problem
Example: Reopen Connecticut, Rules for Operating Summer School During COVID-19, "Detailed Bus Protocols", page 15
Example: NYTimes, "What Back to School Might Look Like in the Age of Covid-19"
|  | Arrival/dismissal | 1. What will student and staff entry and exit at the building look like? Examples: specific/increased entrances, screening protocols, guidelines or design elements to avoid congregation, rainy day/inclement weather plan, etc. 2. What will staff roles and responsibilities be during arrival and dismissal? 3. How will you balance a culture of care/love with the need to efficiently move students through any added screening protocols? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Resource: Equity By Design: Brooklyn LAB Back to School Facilities Toolkit
Example: Comp Sci HS COVID-19 Operations Plan, "Student Arrival" Plan
Example: KY DOE Phase II Reopening Considerations for Facilities, "Drop-off and Dismissal"
Resource: NYTimes, "What Back to School Might Look Like in the Age of Covid-19"
|  | Attendance and enrollment | 1. For distance learners, what will constitute attendance/engagement, and how will this data be tracked and reported by staff? 2. For in-person, how will you log and track movement across the school to ensure ease of contract tracing if needed? Examples: log sheets to enter/exit classrooms, etc. |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Resource: Chalkbeat, "Present or Absent? With schools closed, some districts stop tracking attendance, while others redefine it"
Resource: EdTech Magazine, "How K-12 Schools Monitor Attendance During Remote Learning"
| Building operations | Building updates and upgrades (physical improvements) | 1. What updates/modifications have been made to physical spaces (esp. high-touch or shared spaces and items, such as water fountains)? 2. What additional signage has been added to guide or emphasize health & safety protocols? |  |  | Resource: What Needs to Change Inside School Buildings Before They Reopen
Resource: CDC Considerations for Schools: Operating Schools During COVID-19
Resource: Risk Reduction Strategies for Reopening Schools
Resource: Federation of European Heating, Ventilation, and Air Conditioning Associations, "How to operate and use building services in order to prevent the spread of the coronavirus disease (COVID-19) virus (SARS-CoV-2) in workplaces"
Examples: Transcend Plan: Physical Health and Safety Curated Collection of Plans
Example: Equity By Design: Brooklyn LAB Back to School Facilities Toolkit - Design ideas include suggestions as to how urban schools can modify the physical space on the outside of their buildings to enable safe entry. Suggestions include reimaging space, erecting
|  | Facilities use and space plan | 1. Please list out your classroom capacity and assignments. 2. What will flow of traffic look like throughout the building? 3. How will you increase access to fresh air within the building? |  |  | Example: Social Distancing: Making It Work: A visual on how to incorporate social distancing within a building
Resource: American Institute of Architects: Small Classrooms Setup: Guidance on how to leverage existing classroom features and add new ones to facilitate social distancing
Resource: Equity By Design: Brooklyn LAB Back to School Facilities Toolkit - Brooklyn LAB has provided floor plans and several different layouts for classrooms (e.g. small group, whole group, special needs, etc.) They also include suggestions for intentio
Resource: Risk Reduction Strategies for Reopening Schools
|  | Cleaning and sanitation plan | 1. What will be the typical cleaning schedule? 2. What protocols will individual teachers be following to ensure their classrooms remain sanitary throughout the day? Examples: Expectations and procedures for wipe-downs throughout the day of high-touch surfaces and objects in classroom. |  |  | Example: "Custodial checklist" from KY DOE Phase II Reopening Considerations for Facilities
Example: "Site inventory worksheet" from KY DOE Phase II Reopening Considerations for Facilities
Example: Reopen Connecticut, Rules for Operating Summer School During COVID-19, "Cleaning and Disinfecting", page 10
Example: Urban Act Academy Custodial Run Sheet
|  | Visitor and front office policies | 1. Who is allowed inside the building, and how will they be allowed to enter? 2. How will main office protocols need to adjust? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Example: Comp Sci HS, COVID-19 Operations Plan SY2020-21, "Office Visitor Policy"
| Reimagining & redesigning the in-school experience | Technology | 1. What new or added technology will you need to invest in for carrying out this year's instructional model? What curriculum/technology will you use that can be adapted flexibly across scenarios? 2. What communications to families will you need to make ahead of the school year to prepare students/families for these changes? |  |  | Example: Coney Island Prep Back to School Blueprint, "Techquity" Plan
Resource: Launch Nebraska Step by Step Guide to Launching a Tech Distribution Plan
Example: SFUSD, Device Distribution Communication to Families
Example: Forest Hills Public Schools, "COVID-19 Update: Distribution of Technology to FHPS Students"
|  | Classrooms | 1. How will you set up an in-person classroom to allow for health & safety guidelines? Examples to consider include: student desk setup, common spaces (libraries, carpet/rug, cubbies, lockers), shared items (books, reading assignments) 2. How will you guide teachers on their in-person interactions with students? Examples include: paper distribution, assisting younger children with tasks (like opening food items, zipping up coats), classroom management, student collaboration, student/teacher conferences 3. What communications to families will you need to make ahead of the school year to prepare students/families for these changes? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Example: Comp Sci HS, COVID-19 Operations Plan SY2020-21, "General Classroom Guidelines"
Example: Copenhagen International School, "Use of Materials" Classroom Plan
|  | Meals | 1. What are the protocols to guide how in-school meals (lunch, breakfast, snack) will take place? 2. What is the plan for meal distribution to students in distance learning? 3. What communications to families will you need to make ahead of the school year to prepare students/families for these changes? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Example: Copenhagen International School, "Lunch & Snack" Plan
Example: Sha Tin Junior School, "Lunch and Break Time" Plan
Example: Sha Tin Junior School, Lunch Room Set Up Picture
|  | Recess | 1. How will recess need to change in this scenario? 2. What communications to families will you need to make ahead of the school year to prepare students/families for these changes? |  |  | Resource: Playworks, "How schools can approach recess in the 2020 school year" to plan for COVID-19
Resource: AsphaltGreen, Kids' Games for Social Distancing
Resource: AsphaltGreen, Games Kids Can Plan Independently, Tent Cards
Example: Teacher-created YouTube video to show students how to play safely
Resource: Risk Reduction Strategies for Reopening Schools
|  | Hallways | 1. What new guidelines will inform how students and staff move throughout the building? Examples: one-way hallways, no more bathroom passes, longer transitions between classes, etc. 2. What routines or procedures need to be practiced by students and staff to ensure these guidelines are followed? 3. What are staff roles and responsibilities for monitoring the hallways? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Resource: Equity By Design: Brooklyn LAB Back to School Facilities Toolkit
Example: Comp Sci HS, COVID-19 Operations Plan SY2020-21, "Hallway Transitions/ Transition to Learning Cohorts" Guidance
|  | Bathrooms | 1. How will the bathroom be reconfigured to support physical distancing and hygiene practices? Example: closing off every other stall, converting high-touch surfaces to automatic dispensing, etc. 2. What routines or procedures need to be practiced by students and staff to ensure these guidelines are followed? |  |  | Resource: Risk Reduction Strategies for Reopening Schools
Example: Reopen Connecticut, Rules for Operating Summer School During COVID-19, "Detailed Bathroom Protocols", page 13
Example: Comp Sci HS, COVID-19 Operations Plan SY2020-21, "Bathrooms" Guidance
Resource: FastCompany, "How Coronavirus Could Change Bathrooms for the Better"
|  | Emergency planning | 1. How will fire drills, lockdown/shelter-in-classroom drills, and other drills be different or the same? 2. Map out emergency egress paths against your floorplan, and assign staff coverage to ensure adherence to protocols. |  |  | Example: KY DOE Phase II Reopening Considerations for Facilities, "Emergency Response Drills"
| Fiscal | Budget planning | 1. How will you plan for the short- and long-term budgetary impacts of this crisis? 2. What are the anticipated increases to account for? |  |  | Resource: NSVF COVID-19 Reopening Webinar, Operations and Finance

## 3. Plan Culture
[7 empty] | Complete | In Progress | Not Yet Started
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 3: Plan
Tool: Culture Checklist
Step 1: Default to your top priority scenario, and map out plans that address the components, essential topics, and essential questions in columns C-E below. You may find it helpful to reference the resources listed in Column H. As you plan each component/topic, remember to consider:
- Where can we build for adaptability (flexibility) so that the plans we develop allow us to move between scenarios without significant rework? (i.e., flex weeks) - Where do we need to reserve the right to play (build out several contingencies) by considering what distinct planning might be necessary across the multiple scenarios? (budget scenario planning in response to 1%, 3%, or 5% cuts)
Step 2: Determine where you will document and store your plans. Many teams we work with like to create a single folder on a shared drive. If that makes sense for your team, link the folder or section of the master deliverable in Column G.
Step 3: Once you have addressed all components within this plan for your top priority scenario, now consider your secondary/alternate scenario:
- identify which components of this plan are most critical to build additional contingency plans in, vs. which will be flexible enough to hold across scenarios; build out those contingency plans where necessary.
Note: If you would like additional details to support answering the Essential Questions listed in Column E, please refer to this Google Sheet.
Plan | Component | Essential Topics | Essential Questions to Address | Status | Link to Deliverable or Section of Master Plan | Key Resources
Culture | School culture | Essential components of student experience | 1. What are the essential components and outcomes of a student's experience that must hold true for culture this year, regardless of scenario (e.g., celebrating birthdays, culture of care)? How can you translate some or all of these experiences to a different setting? 2. In particular, what character habits, skills, or student outcomes need to be of particular focus this school year — i.e., resilience, reflection, self-love? | Not Yet Started |  | Resource: NSVF COVID-19 Reopening Webinar, Culture
Resource: Bellwether Culture Framework
Resource: Instruction Partners' Culture Planning Tool
Resource: IDEA Public Schools, A Day in the Life of Ms. Brenda Carranza's Story (Case Study)
Resource: IDEA Public Schools, Annie Garza's First Day of School (Case Study)
Example: Coney Island Prep, Back to School Blueprint, "Introduction"
|  | Mindsets & beliefs | 1. What foundational ideas do you want to align your team around this year? 2. What mindsets on race & equity and supporting students & families with trauma do you want to align your team around this year? | In Progress |  | Resource: NSVF COVID-19 Reopening Webinar, Culture
Resource: Instruction Partners' Culture Planning Tool
Resource: IDEA Public Schools, A Day in the Life of Ms. Brenda Carranza's Story (Case Study)
Resource: IDEA Public Schools, Annie Garza's First Day of School (Case Study)
Example: Comp Sci HS, Guiding Principles: "Culture & Investment"
|  | Methods and systems for building staff culture | 1. In this new socially distanced/virtual/hybrid setting, what strategies will you employ to build strong culture among adults? This could include: intentional attention to relationships across grade levels, mentoring, calendar with milestones and celebrations, etc. 2. In the BOY especially, what is your approach to intentionally ramp up culture? 3. How will you ensure staff feel safe and cared for upon return? | Complete |  | Resource: NSVF COVID-19 Reopening Webinar, Culture
Resource: Instruction Partners' Culture Planning Tool
Resource: The School Leader's Tool For Assessing and Improving School Culture (MSSAA)
Resource: Community School Climate Self-Assessment Tool
Resource: How to Roll Out a Virtual Platform with Teachers and Students (ANet)
Resource: Whetstone Education Tips for Providing SEL Support to Teachers during Distance Learning
|  | Methods and systems for building student culture | 1. In this new socially distanced/virtual/hybrid setting, what strategies will you employ to build culture among students? This could include: accountability for checking in with students; strategies for virtual culture-building; calendar with milestones and celebrations, etc. 2. In the BOY especially, what is your approach to intentionally ramp up culture? 3. How will you reinforce school values, introduce new rituals and routines, process trauma, ensure high levels of engagement, and deliver meaningful SEL supports? 4. How will you ensure students feel safe and cared for upon return? |  |  | Resource: NSVF COVID-19 Reopening Webinar, Culture
Resource: Instruction Partners' Culture Planning Tool
Resource: Community School Climate Self-Assessment Tool
Resource: National Institute for STEM Education: Online Classroom Routines
Resource: PBS: 5 Virtual Ways to Build a Classroom Community
Resource: How to Roll Out a Virtual Platform with Teachers and Students (ANet)
Resource: TLAC blog - Resources for Virtual Engagement
Example: Comp Sci HS, Instructional Design - "Advisory Plan"
| Staff and student supports | Wellness supports for staff | 1. How will you surface and address the biggest concerns from your staff about returning to the classroom (e.g., unrealistic expectations, socioemotional health issues, layoffs or budget cuts)? 2. Leaders understand the need for an intentional and increased focus on mental health and wellness for staff this year. What are the strategies you will use to support staff's mental health and well-being? What are the ways you will check in with staff (e.g., surveys, check-ins) to get a "pulse check" on their well-being throughout the year? 3. How will you support collective healing and community building — both during PD, and into the school year? |  |  | Resource: National Child Traumatic Stress Network, Secondary Traumatic Stress for Educators
Resource: Secondary Traumatic Stress and Self-Care Packet for Staff
Resource: Ten Strategies for Educators' Wellbeing: A Handbook for Schools During the COVID-19 Outbreak
Resource: National Center for School Mental Health
Resource: Whetstone Education Tips for Providing SEL Support to Teachers during Distance Learning
Resource: Coping with the Death of a Student or Staff Member
Resource: Strong Start Communication Guidance for Principals
Example: Ideas for Maintaining Connection Among Staff During Distance Learning (Montessori For All: Distance Learning for Equity Plan)
|  | Wellness supports for students | 1. What (nonacademic) supports will you put in place for students to be able to access learning? E.g., meal distribution, tech/remote learning support, SEL resources for parents/families, etc. 2. What are the ways you will check in with students and families to get a "pulse check" throughout the year? |  |  | Resource: COVID-19 SEL Resource Bank (West Ed)
Resource: COVID-19 SEL Resource Bank (CASEL)
Resource: Responding to Change and Loss (National Alliance for Grieving Children)
Resource: Student Questionnaire (CCEE)
Resource: Class Check In Survey (CCEE)
Resource: Child Trauma Toolkit for Educators
Example: Impact Public Schools SEL Model for Distance Learning: "Mentor Time"
Example: COVID-19 Student-Teacher Wellness Checks & Conversation Roadmap
Example: Coney Island Prep, Back to School Blueprint, "Trauma-Informed Practices"
| Student, family, and community engagement | Family communications and engagement plan | 1. How will you engage all families as partners in their children's learning, SEL development, and school community? 2. How frequently and through which methods will you build relationships with families throughout the pandemic? |  |  | Resource: Getting Started with REAL Family Engagement During Distance Learning (Flamboyan Foundation)
Example: Coney Island Prep, Back to School Blueprint, Family Engagement & Support Plans
Resource: Strategies to Engage Unreached Families During COVID-19 (Flamboyan)
Resource: Family Wellness Check In Guidance (Flamboyan)
|  | Setting up remote learning plan for remote/disconnected families | 1. What supports will students/families need to be able to access learning? E.g., Wifi hotspots, laptops, data plans, printed packets of materials, etc. 2. How will you utilize any in-person time to set up students/families for virtual learning, if needed? 3. What data will you collect and how will you track student/family engagement at home? |  |  | Example: Coney Island Prep Back to School Blueprint, "Techquity" Plan
Resource: Launch Nebraska Step by Step Guide to Launching a Tech Distribution Plan
Example: SFUSD, Device Distribution Communication to Families
Example: Forest Hills Public Schools, "COVID-19 Update: Distribution of Technology to FHPS Students"
|  | Family/student policies and procedures | 1. What policies and procedures for student & family expectations should be revisited in light of COVID-19? 2. How will any changes in policy be communicated to students and families, and how will you support students and families to meet any new/different expectations? |  |  | Example: YES Prep Reopening Guide For Families
Resource: Strong Start Communication Guidance for Principals

## 3. Plan Academics
[7 empty] | Complete | In Progress | Not Yet Started
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 3: Plan
Tool: Academics Checklist
Step 1: Default to your top priority scenario, and map out plans that address the components, essential topics, and essential questions in columns C-E below. You may find it helpful to reference the resources listed in Column H. As you plan each component/topic, remember to consider:
- Where can we build for adaptability (flexibility) so that the plans we develop allow us to move between scenarios without significant rework? (i.e., flex weeks) - Where do we need to reserve the right to play (build out several contingencies) by considering what distinct planning might be necessary across the multiple scenarios? (budget scenario planning in response to 1%, 3%, or 5% cuts)
Step 2: Determine where you will document and store your plans. Many teams we work with like to create a single folder on a shared drive. If that makes sense for your team, link the folder or section of the master deliverable in Column G.
Step 3: Once you have addressed all components within this plan for your top priority scenario, now consider your secondary/alternate scenario:
- identify which components of this plan are most critical to build additional contingency plans in, vs. which will be flexible enough to hold across scenarios; build out those contingency plans where necessary.
Note: If you would like additional details to support answering the Essential Questions listed in Column E, please refer to this Google Sheet.
Plan | Component | Essential Topics | Essential Questions to Address | Status | Link to Deliverable or Section of Master Plan | Key Resources
Academics | Instructional model | Essential components of the student experience | 1. What are the essential components and outcomes of a student's academic experience that must hold true this year, regardless of scenario? 2. In particular, what academic experiences need to be of particular focus this school year — i.e., assessment from last spring? | Not Yet Started |  | Resource: NSVF COVID-19 Reopening Webinar, Academics
Resource: Priority Checklist: Key Components of a Distance Learning School Day (CCEE)
Resource: Priority Checklist: Key Components of a Hybrid Learning School Day (CCEE)
Resource: Key Components of Recovery to Reinvention Plan: Description of Student + Staff Experience (Transcend)
Resource: Addressing Unfinished Learning After COVID-19 School Closures
|  | Mindsets & beliefs | 1. What foundational ideas do you want to align your team around this year? 2. What mindsets on race & equity and supporting students & families with trauma do you want to to align your team around this year? | In Progress |  | Resource: NSVF COVID-19 Reopening Webinar, Academics
|  | Content/curriculum plan | 1. What is your plan to deliver content (core, specials, enrichment)? Particularly if virtual, how will you connect with and engage learners? 2. What is your plan to assess and address students' progress from last spring? | Complete |  | Resource: NSVF COVID-19 Reopening Webinar, Academics
Resource: 2020–21 Priority Instructional Content in English Language Arts/Literacy and Mathematics (Achieve the Core)
Resource: 4 Dimensions of Instructional Materials Strategy (Achievement Network)
Resource: Roadmap for Shifting to At-Home Learning (TNTP)
Resource: Schedule Guide for At-Home Learning (TNTP)
|  | Delivery format/ instructional expectations | 1. What expectations will you need to set to ensure quality instruction within your delivery format (virtual, in-person)? 2. What are the high-leverage instructional practices you will prioritize within this delivery format? (e.g., modeling & guided practice, small group instruction, conferencing and providing feedback) |  |  | Resource: Instructional Models: Choosing a Distance Learning Model (Instruction Partners)
Resource: ELA Guidelines for Distance Learning Models (Instruction Partners)
Resource: Math Guidelines for Distance Learning Models (Instruction Partners)
Example: Comp Sci HS, Instructional Design - "Classes"
Resource: How to Roll Out a Virtual Platform with Teachers and Students (ANet)
Resource: Success Academy's Approach to Remote Learning
|  | Other components of instructional model | 1. Assessment: How will formative and summative assessment need to look different within your delivery format? 2. Grading/accountability: What are the expectations for graded work submitted via distance learning? 3. Data-driven instruction: What high-leverage data can you leverage now to create intervention groups? What data collection will you prioritize to make instructional decisions during the school year and ensure a system for rapid data cycles? |  |  | Resource: 3 Principles for Assessments during Instructional Recovery and Beyond (Achievement Network)
Resource: Assessing for Learning (The Learning Accelerator)
Resource: Accountability and Feedback Online (Teach Like A Champion)
Resource: Checks for Understanding in a Distance Learning Envrionment
Resource: NSVF COVID-19 Reopening Webinar, Academics
| Schedule and staffing | Master schedule and staffing plan | Include a master bell schedule to lay out students and staff day, including start/end times (and where staggered starts/dismissals apply), common space utilization (outdoor space, cafeteria, gym, auditorium), and instructional minutes. |  |  | Resource: Hybrid School Schedules: More Flexibility; Big Logistical Challenges (EdWeek)
Resource: Pulling Off a Regular School Schedule—With Modifications—in the Pandemic (EdWeek)
Resource: Education Resource Strategies, COVID Decision Points
Resource: Key Components of Recovery to Reinvention Plan: Master Schedule + Facilities Plan (Trascend)
Resource: EmpowerK12, "Our thoughts on school schedules for a 2020-21 reboot"
Example: Comp Sci HS, Instructional Design - "Classes"
Example: Comp Sci HS, Instructional Design - "Weekly Schedule"
Resource: A Practical Guide to Common Bell Schedules (And Free Bell Schedule Builder Tool) (Abl)
|  | Coverage plans | 1. What is the coverage plan for highly trafficked times/areas? 2. What extra capacity have you built into your staffing to provide flexibility as situations arise? |  |  | Example: Comp Sci HS, COVID-19 Operations Plan SY2020-21, "Hallway Transitions/ Transition to Learning Cohorts" Guidance
| Student instructional supports | Intervention, ELL, SpEd, and other academic student supports | 1. How will the essential student experience look different for students with different profiles? (e.g., younger students, older students, students with special needs, ELL, students with Tier 2/3 academic or social-emotional needs, unique courses such as AP or CTE or place-based or internships, etc.) 2. What is the plan for supporting ELL, special education, and any other students with special needs? |  |  | Resource: School Closure Toolkit for Districts: Special Populations (Tennessee DOE)
Resource: Supporting English Language Learners during School Closures (TNTP)
Resource: Supporting Students with Diverse Learning Needs at Home (TNTP)
Resource: Resources for Supporting Learners with Disabilities (Digital Promise)
Example: Comp Sci HS, Instructional Design - "Overview of Differentiation and Support"

## 3. Plan Talent
[7 empty] | Complete | In Progress | Not Yet Started
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 3: Plan
Tool: Talent Checklist
Step 1: Default to your top priority scenario, and map out plans that address the components, essential topics, and essential questions in columns C-E below. You may find it helpful to reference the resources listed in Column H. As you plan each component/topic, remember to consider:
- Where can we build for adaptability (flexibility) so that the plans we develop allow us to move between scenarios without significant rework? (i.e., flex weeks) - Where do we need to reserve the right to play (build out several contingencies) by considering what distinct planning might be necessary across the multiple scenarios? (budget scenario planning in response to 1%, 3%, or 5% cuts)
Step 2: Determine where you will document and store your plans. Many teams we work with like to create a single folder on a shared drive. If that makes sense for your team, link the folder or section of the master deliverable in Column G.
Step 3: Once you have addressed all components within this plan for your top priority scenario, now consider your secondary/alternate scenario:
- identify which components of this plan are most critical to build additional contingency plans in, vs. which will be flexible enough to hold across scenarios; build out those contingency plans where necessary.
Note: If you would like additional details to support answering the Essential Questions listed in Column E, please refer to this Google Sheet.
Plan | Component | Essential Topics | Essential Questions | Status | Link to Deliverable or Section of Master Plan | Key Resources
Talent | Staff policies and procedures | Addressing COVID concerns for at-risk/ high-risk groups | 1. How have staff been contacted thus far? How has school leadership sought out staff input? 2. What are your expectations for staff to return in person, and how do these map against the protections and accommodations they are ensured via federal policy (FMLA, FFCRA, ADA)? 3. What is your request and approval protocol for those who would like to apply for accommodations or leave? | Not Yet Started |  | Resource & Example: Achievement First, School Staff Expectations
Example: Coney Island Prep, Back to School Blueprint, "Staffing & Support"
Resource: National School Boards Association, A Legal Guide for School Leaders
|  | Addressing potential personnel shortages | 1. What will be your coverage and substitute procedures? 2. Will there be an extended substitute pool, given the ramifications of teacher shortages on social distancing? 3. How can you partner with the district or other community resources to expand your sub pool? | In Progress |  | Resource: Recognizing Substitute Staff During COVID-19
|  | Updates to HR/ handbook policies | 1. How do existing HR protocols (e.g., calling in sick, tracking leave) change related to COVID-19? 2. Will staff be required to use their sick days, PTO, or be granted additional days if out sick with COVID-19? | Complete |  | Resource: National School Boards Association, A Legal Guide for School Leaders
Resource: Achievement First School Staff Expectations, Appendix: HR/Legal Requirements
Example: Coney Island Prep, Back to School Blueprint, "Staffing & Support"
|  | Hiring and onboarding | 1. How will you shift any part of the talent acquisition process (e.g., in-person interviews, sample lessons) to be either virtual or socially distanced? 2. How will onboarding (e.g., mentoring, shadowing, orientation) need to look different? |  |  | Resource: NSVF COVID-19 Reopening Webinar, Talent
Resource: TNTP's Best Practices for Virtual Interviews
Resource: TNTP's Ideas for Virtual Demo Lessons
Resource: TNTP's Virtual Onboarding and Cultivation Guide
Resource: TNTP's Virtual Talent Guide
| Professional development and support* | Professional development structures and instructional supports | 1. What are your professional development priorities for the beginning of the year — what is a limited, clear, attainable set of goals to achieve in your PD plan? 2. What additional PD and instructional supports will you need to plan for so staff are prepared to deliver instruction in your new setting? 3. How will you continue to push knowledge growth and development with your teachers? |  |  | Resource: Suggestions for Teacher Support and Professional Development During COVID (CCEE)
Resource: How to Roll Out a Virtual Platform with Teachers and Students (ANet)
Example: New Staff PD Schedule (DSST)
Example: National Network of State Teachers of the Year, Zoom Facilitation Playbook
Resource: NSVF COVID-19 Reopening Webinar, Talent
Example: Comp Sci HS, "Phase 1: Adult Preparation"
Example: Coney Island Prep, Back to School Blueprint
|  | Instructional coaching plan | 1. What is your existing instructional coaching plan to support teacher development, and how will it need to be adjusted to support your new setting? 2. How will observations, coaching, and feedback occur? |  |  | Resource: NSVF COVID-19 Reopening Webinar, Academics
Resource: Suggestions for Teacher Support and Professional Development During COVID (CCEE)
*Note: Included here are strategies for supporting staff instructionally; however, we also recognize the significant need to support staff’s emotional and mental health and well-being. These strategies are separately outlined in the “Staff and student supports” section of the Culture plan.

## 4. Communicate
Completing Your 2020-21 Reopening Plan: A Practical Workbook for School Leaders
Step 4: Communicate
Tool: Communications Plan
Step 1: Revise the list of stakeholders provided in Column B to reflect the most important stakeholders for your broader community.
- This list should include both internal stakeholders (such as families, staff, and students) and external stakeholders (such as community partners, public health officials, or district leadership) you will need to update before reopening.
Step 2: Reflect on how you want each stakeholder group (internal and external) to feel at the end of their communication with you. Record in Column C.
Step 3: Consider both your answers to Column C and the below questions for each stakeholder group, to draft key messages in Column D.
- What do they need to know from this plan? (e.g., staff will need to know the policies for requesting leave or accommodations.) - What do I seek to know from them (if anything)? (e.g., I seek to get buy-in from instructional coaches on our approach to socioemotional supports for teachers.)
Step 4: Determine the portion of the plan to share/build off of, when and how to share, and the owner for each of these key messages.
Stakeholders | What Must Be Communicated? | When Must Communication Happen? | Portion(s) of Plan to Share or Build Off Of | How Will it be Communicated? | Owner
Teachers + Staff
Families
Students
District Central Office
Public Health Organizations
Community Partner Organizations